## Jena-Horschel
From | To | Milepost | Actual Section Length (mi) | Section Difficulty | Effective Section Length | Cum Eff Length Dn | Match Row Dn | Match Miles Dn | Cum Miles Done Month Dn | Miles Needed in Completion Month | Rate in Completion Month | First Date Completion Month | Days Since Start | Working Down Completion Date | Cum Eff Length Up | Match Row Up | Match Miles Up | Cum Miles Done Month Up | Miles Needed in Completion Month | Rate in Completion Month | First Date in Completion Month | Days Since Start | Working Up Completion Date
Start Date, Working Down Line |  | 0 |  |  | 0 | 0 | 15 |  | -80.1786 |  |  | 1933-03-01 |  | 1933-03-01
[9 empty] | 0 |  |  |  |  | 0
Jena | Weimar | 2.7 | 2.7 | 1 | 2.7 | 2.7 | 16 | 82.8786 | 87.9286 | 2.7 | 1.75 | 1933-03-01 | 10.8 | 1933-03-10 19:12 | 35 | 17 | 89.4643 | 95.4286 | 1.5357 | 1.75 | 1933-04-01 | 6.1429 | 1933-04-06 03:26
Weimar | Erfurt | 17.2 | 14.5 | 1 | 14.5 | 17.2 | 18 | 97.3786 | 103.1786 | 1.95 | 1.75 | 1933-05-01 | 7.8 | 1933-05-07 19:12 | 32.3 | 16 | 86.7643 | 87.9286 | 6.5857 | 1.75 | 1933-03-01 | 26.3429 | 1933-03-26 08:14
Erfurt | Gotha | 19.7 | 2.5 | 1 | 2.5 | 19.7 | 18 | 99.8786 | 103.1786 | 4.45 | 1.75 | 1933-05-01 | 17.8 | 1933-05-17 19:12 | 17.8 | 14 | 72.2643 | 74.1786 | 4.7286 | 1.5 | 1933-01-01 | 22.0667 | 1933-01-22 01:36
Gotha | Eisenach | 21.5 | 1.8 | 1 | 1.8 | 21.5 | 18 | 101.6786 | 103.1786 | 6.25 | 1.75 | 1933-05-01 | 25 | 1933-05-25 | 15.3 | 14 | 69.7643 | 74.1786 | 2.2286 | 1.5 | 1933-01-01 | 10.4 | 1933-01-10 09:36
Eisenach | Horschel | 35 | 13.5 | 1 | 13.5 | 35 | 20 | 115.1786 | 118.4286 | 4.5 | 1.75 | 1933-07-01 | 18 | 1933-07-18 | 13.5 | 14 | 67.9643 | 74.1786 | 0.42857 | 1.5 | 1933-01-01 | 2 | 1933-01-02
Start Date, Working Up Line |  |  |  |  | 0 | 0 | [8 empty] | 0 | 11 |  | -54.4643 |  |  | 1932-11-01 |  | 1932-11-01
[14 empty] | 1 |  |  |  | 0 |  |  |  |  | 0
Section Difficulty: 1 is average difficulty so normal tracklaying rate; higher #s more difficult so rate slower
Enter tracklaying rates for each month on MonthRates page
Enter start date in form MM/DD/19YY
spreadsheet created by Iver Cooper.
Formulas:
First Date Completion Month = DATE(YEAR([Working Down Completion Date]),MONTH([Working Down Completion Date]),1)
First Date Completion Month = OFFSET(MonthRates!$A6,[Match Row Dn]-2,0,1,1)
Working Down Completion Date = [First Date Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
First Date in Completion Month = OFFSET(MonthRates!$A6,[Match Row Up]-2,0,1,1)
First Date in Completion Month = DATE(YEAR([Working Up Completion Date]),MONTH([Working Up Completion Date]),1)
Working Up Completion Date = [First Date in Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
Note on K1: Iver Cooper: Can be neg if start and complete in same mo and start after 1st.
Note on H2: Iver Cooper: row of prior month, no +1 because this has to be exact match
Note on J2: Iver Cooper: lost miles = end of month prior to start month
Note on M2: Iver Cooper: first day of start month
Note on J3: Iver Cooper: lost miles from day 1 of start month to day before start
Note on O3: Iver Cooper: lost days in start month
Note on Q4: Iver Cooper: +1 is wrong if lookup value = match value
Note on Q9: Iver Cooper: no +1 because this has to be exact match

## Jena-Gera
From | To | Milepost | Actual Section Length (mi) | Section Difficulty | Effective Section Length | Cum Eff Length Dn | Match Row Dn | Match Miles Dn | Cum Miles Done Month Dn | Miles Needed in Completion Month | Rate in Completion Month | First Date Completion Month | Days Since Start | Working Down Completion Date | Cum Eff Length Up | Match Row Up | Match Miles Up | Cum Miles Done Month Up | Miles Needed in Completion Month | Rate in Completion Month | First Date in Completion Month | Days Since Start | Working Up Completion Date
Start Date, Working Down Line |  | 0 |  |  | 0 | 0 | 15 |  | -80.1786 |  |  | 1933-03-01 |  | 1933-03-01
[9 empty] | 0 |  |  |  |  | 0 | 0
Jena | Hermsdorf | 12.5 | 12.5 | 1 | 12.5 | 12.5 | 17 | 92.6786 | 95.4286 | 4.75 | 1.75 | 1933-04-01 | 19 | 1933-04-19 | 23 | 15 | 77.4643 | 80.1786 | 3.2857 | 1.5 | 1933-02-01 | 15.3333 | 1933-02-15 08:00
Hermsdorf | Gera | 23 | 10.5 | 1 | 10.5 | 23 | 18 | 103.1786 | 103.1786 | 7.75 | 1.75 | 1933-05-01 | 31 | 1933-05-31 | 10.5 | 13 | 64.9643 | 67.5357 | 4.0714 | 1.5 | 1932-12-01 | 19 | 1932-12-19
Start Date, Working Up Line |  |  |  |  | 0 | 0 | [8 empty] | 0 | 11 |  | -54.4643 |  |  | 1932-11-01 |  | 1932-11-01
[14 empty] | 1 |  |  |  | 0 |  |  |  |  | 0
Section Difficulty: 1 is average difficulty so normal tracklaying rate; higher #s more difficult so rate slower
Enter tracklaying rates for each month on MonthRates page
Enter start date in form MM/DD/19YY
spreadsheet created by Iver Cooper.
Formulas:
First Date Completion Month = DATE(YEAR([Working Down Completion Date]),MONTH([Working Down Completion Date]),1)
First Date Completion Month = OFFSET(MonthRates!$A6,[Match Row Dn]-2,0,1,1)
Working Down Completion Date = [First Date Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
First Date in Completion Month = OFFSET(MonthRates!$A6,[Match Row Up]-2,0,1,1)
First Date in Completion Month = DATE(YEAR([Working Up Completion Date]),MONTH([Working Up Completion Date]),1)
Working Up Completion Date = [First Date in Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])

## GV-Nurnberg
From | To | Milepost | Actual Section Length (mi) | Section Difficulty | Effective Section Length | Cum Eff Length Dn | Match Row Dn | Match Miles Dn | Cum Miles Done Month Dn | Miles Needed in Completion Month | Rate in Completion Month | First Date Completion Month | Days Since Start | Working Down Completion Date | Cum Eff Length Up | Match Row Up | Match Miles Up | Cum Miles Done Month Up | Miles Needed in Completion Month | Rate in Completion Month | First Date in Completion Month | Days Since Start | Working Up Completion Date
Start Date, Working Down Line |  | 0 |  |  | 0 | 0 | 38 |  | -216.7857 |  |  | 1935-02-01 |  | 1935-02-01
[9 empty] | 0 |  |  |  |  | 0
Grantville | Saalfeld | 2.7 | 2.7 | 1 | 2.7 | 2.7 | 39 | 219.4857 | 222.7857 | 2.7 | 1.5 | 1935-02-01 | 12.6 | 1935-02-12 14:24 | 117 | 55 | 333.7857 | 339.3571 | 1.9286 | 1.75 | 1936-06-01 | 7.7143 | 1936-06-07 17:09
Saalfeld | Probsizella | 17.2 | 14.5 | 1 | 14.5 | 17.2 | 41 | 233.9857 | 238.0357 | 3.45 | 1.75 | 1935-04-01 | 13.8 | 1935-04-13 19:12 | 114.3 | 54 | 331.0857 | 331.8571 | 6.9786 | 1.75 | 1936-05-01 | 27.9143 | 1936-05-27 21:57
Probsizella | Lauerstein | 19.7 | 2.5 | 1 | 2.5 | 19.7 | 41 | 236.4857 | 238.0357 | 5.95 | 1.75 | 1935-04-01 | 23.8 | 1935-04-23 19:12 | 99.8 | 52 | 316.5857 | 316.6071 | 6.6214 | 1.5 | 1936-03-01 | 30.9 | 1936-03-30 21:36
Lauerstein | Ludwigsstadt | 21.5 | 1.8 | 1 | 1.8 | 21.5 | 42 | 238.2857 | 245.7857 | 0.25 | 1.75 | 1935-05-01 | 1 | 1935-05-01 | 97.3 | 52 | 314.0857 | 316.6071 | 4.1214 | 1.5 | 1936-03-01 | 19.2333 | 1936-03-19 05:36
Ludwigsstadt | Rothenkirchen | 35 | 13.5 | 1 | 13.5 | 35 | 43 | 251.7857 | 253.2857 | 6 | 1.75 | 1935-06-01 | 24 | 1935-06-24 | 95.5 | 52 | 312.2857 | 316.6071 | 2.3214 | 1.5 | 1936-03-01 | 10.8333 | 1936-03-10 20:00
Rothenkirchen | Stockheim | 39 | 4 | 1 | 4 | 39 | 44 | 255.7857 | 261.0357 | 2.5 | 1.75 | 1935-07-01 | 10 | 1935-07-10 | 82 | 50 | 298.7857 | 303.75 | 1.6786 | 1.5 | 1936-01-01 | 7.8333 | 1936-01-07 20:00
Stockheim | Kronach | 44 | 5 | 1 | 5 | 44 | 44 | 260.7857 | 261.0357 | 7.5 | 1.75 | 1935-07-01 | 30 | 1935-07-30 | 78 | 49 | 294.7857 | 297.1071 | 4.3214 | 1.5 | 1935-12-01 | 20.1667 | 1935-12-20 04:00
Kronach | Hochstadt | 55 | 11 | 1 | 11 | 55 | 46 | 271.7857 | 276.2857 | 3 | 1.75 | 1935-09-01 | 12 | 1935-09-12 | 73 | 48 | 289.7857 | 290.4643 | 5.75 | 1.5 | 1935-11-01 | 26.8333 | 1935-11-26 20:00
Hochstadt | Michelau | 56 | 1 | 1 | 1 | 56 | 46 | 272.7857 | 276.2857 | 4 | 1.75 | 1935-09-01 | 16 | 1935-09-16 | 62 | 47 | 278.7857 | 284.0357 | 2.5 | 1.75 | 1935-10-01 | 10 | 1935-10-10
Michelau | Lichtenfels | 58 | 2 | 1 | 2 | 58 | 46 | 274.7857 | 276.2857 | 6 | 1.75 | 1935-09-01 | 24 | 1935-09-24 | 61 | 47 | 277.7857 | 284.0357 | 1.5 | 1.75 | 1935-10-01 | 6 | 1935-10-06
Lichtenfels | Hallstadt | 77 | 19 | 1 | 19 | 77 | 49 | 293.7857 | 297.1071 | 3.3214 | 1.5 | 1935-12-01 | 15.5 | 1935-12-15 12:00 | 59 | 46 | 275.7857 | 276.2857 | 7 | 1.75 | 1935-09-01 | 28 | 1935-09-28
Hallstadt | Bamberg | 78 | 1 | 1 | 1 | 78 | 49 | 294.7857 | 297.1071 | 4.3214 | 1.5 | 1935-12-01 | 20.1667 | 1935-12-20 04:00 | 40 | 44 | 256.7857 | 261.0357 | 3.5 | 1.75 | 1935-07-01 | 14 | 1935-07-14
Bamberg | Hirschaid | 85 | 7 | 1 | 7 | 85 | 50 | 301.7857 | 303.75 | 4.6786 | 1.5 | 1936-01-01 | 21.8333 | 1936-01-21 20:00 | 39 | 44 | 255.7857 | 261.0357 | 2.5 | 1.75 | 1935-07-01 | 10 | 1935-07-10
Hirschaid | Eggelsheim | 89 | 4 | 1 | 4 | 89 | 51 | 305.7857 | 309.9643 | 2.0357 | 1.5 | 1936-02-01 | 9.5 | 1936-02-09 12:00 | 32 | 43 | 248.7857 | 253.2857 | 3 | 1.75 | 1935-06-01 | 12 | 1935-06-12
Eggelsheim | Forchheim | 93 | 4 | 1 | 4 | 93 | 51 | 309.7857 | 309.9643 | 6.0357 | 1.5 | 1936-02-01 | 28.1667 | 1936-02-28 04:00 | 28 | 42 | 244.7857 | 245.7857 | 6.75 | 1.75 | 1935-05-01 | 27 | 1935-05-27
Forchheim | Erlangen | 103 | 10 | 1 | 10 | 103 | 53 | 319.7857 | 324.1071 | 3.1786 | 1.75 | 1936-04-01 | 12.7143 | 1936-04-12 17:09 | 24 | 42 | 240.7857 | 245.7857 | 2.75 | 1.75 | 1935-05-01 | 11 | 1935-05-11
Erlangen | Furth | 112 | 9 | 1 | 9 | 112 | 54 | 328.7857 | 331.8571 | 4.6786 | 1.75 | 1936-05-01 | 18.7143 | 1936-05-18 17:09 | 14 | 41 | 230.7857 | 238.0357 | 0.25 | 1.75 | 1935-04-01 | 1 | 1935-04-01
Furth | Nurnberg | 117 | 5 | 1 | 5 | 117 | 55 | 333.7857 | 339.3571 | 1.9286 | 1.75 | 1936-06-01 | 7.7143 | 1936-06-07 17:09 | 5 | 39 | 221.7857 | 222.7857 | 5 | 1.5 | 1935-02-01 | 23.3333 | 1935-02-23 08:00
Start Date, Working Up Line |  |  |  |  | 0 | 0 | [8 empty] | 0 | 38 |  | -216.7857 |  |  | 1935-02-01 |  | 1935-02-01
[14 empty] | 1 |  |  |  | 0 |  |  |  |  | 0
Section Difficulty: 1 is average difficulty so normal tracklaying rate; higher #s more difficult so rate slower
Enter tracklaying rates for each month on MonthRates page
Enter start date in form MM/DD/19YY
spreadsheet created by Iver Cooper.
Formulas:
First Date Completion Month = DATE(YEAR([Working Down Completion Date]),MONTH([Working Down Completion Date]),1)
First Date Completion Month = OFFSET(MonthRates!$A6,[Match Row Dn]-2,0,1,1)
Working Down Completion Date = [First Date Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
First Date in Completion Month = OFFSET(MonthRates!$A6,[Match Row Up]-2,0,1,1)
First Date in Completion Month = DATE(YEAR([Working Up Completion Date]),MONTH([Working Up Completion Date]),1)
Working Up Completion Date = [First Date in Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
Note on K1: Iver Cooper: Can be neg if start and complete in same mo and start after 1st.
Note on H2: Iver Cooper: row of prior month, no +1 because this has to be exact match
Note on J2: Iver Cooper: lost miles = end of month prior to start month
Note on M2: Iver Cooper: first day of start month
Note on J3: Iver Cooper: lost miles from day 1 of start month to day before start
Note on O3: Iver Cooper: lost days in start month
Note on Q4: Iver Cooper: +1 is wrong if lookup value = match value
Note on Q22: Iver Cooper: no +1 because this has to be exact match

## GV-Magdeburg
From | To | Milepost | Actual Section Length (mi) | Section Difficulty | Effective Section Length | Cum Eff Length Dn | Match Row Dn | Match Miles Dn | Cum Miles Done Month Dn | Miles Needed in Completion Month | Rate in Completion Month | First Date Completion Month | Days Since Start | Working Down Completion Date | Cum Eff Length Up | Match Row Up | Match Miles Up | Cum Miles Done Month Up | Miles Needed in Completion Month | Rate in Completion Month | First Date in Completion Month | Days Since Start | Working Up Completion Date | Two end date at B column station
Start Date, Working Down Line |  | 0 |  |  | 0 | 0 | 11 |  | -54.4643 |  |  | 1932-11-01 |  | 1932-11-01
[9 empty] | 0 |  |  |  |  | 0
Grantville | Rudolstadt | 2.9 | 2.9 | 1 | 2.9 | 2.9 | 12 | 57.3643 | 60.8929 | 2.9 | 1.5 | 1932-11-01 | 13.5333 | 1932-11-13 12:48 | 158 | 50 | 301.5714 | 303.75 | 4.4643 | 1.5 | 1936-01-01 | 20.8333 | 1936-01-20 20:00 | 1932-11-13 12:48
Rudolstadt | Jena | 27.8 | 24.9 | 1 | 24.9 | 27.8 | 16 | 82.2643 | 87.9286 | 2.0857 | 1.75 | 1933-03-01 | 8.3429 | 1933-03-08 08:14 | 155.1 | 50 | 298.6714 | 303.75 | 1.5643 | 1.5 | 1936-01-01 | 7.3 | 1936-01-07 07:12 | 1933-03-08 08:14
Jena | Bad Kosen | 40.75 | 12.95 | 1 | 12.95 | 40.75 | 17 | 95.2143 | 95.4286 | 7.2857 | 1.75 | 1933-04-01 | 29.1429 | 1933-04-29 03:26 | 130.2 | 46 | 273.7714 | 276.2857 | 4.9857 | 1.75 | 1935-09-01 | 19.9429 | 1935-09-19 22:38 | 1933-04-29 03:26
Bad Kosen | Naumberg | 56 | 15.25 | 1 | 15.25 | 56 | 19 | 110.4643 | 110.6786 | 7.2857 | 1.75 | 1933-06-01 | 29.1429 | 1933-06-29 03:26 | 117.25 | 44 | 260.8214 | 261.0357 | 7.5357 | 1.75 | 1935-07-01 | 30.1429 | 1935-07-30 03:26 | 1933-06-29 03:26
Naumberg | Weissenfels | 63.5 | 7.5 | 1 | 7.5 | 63.5 | 20 | 117.9643 | 118.4286 | 7.2857 | 1.75 | 1933-07-01 | 29.1429 | 1933-07-29 03:26 | 102 | 42 | 245.5714 | 245.7857 | 7.5357 | 1.75 | 1935-05-01 | 30.1429 | 1935-05-30 03:26 | 1933-07-29 03:26
Weissenfels | Merseburg | 74.75 | 11.25 | 1 | 11.25 | 74.75 | 25 | 129.2143 | 129.5 | 3.0357 | 0.75 | 1933-12-01 | 28.3333 | 1933-12-28 08:00 | 94.5 | 42 | 238.0714 | 245.7857 | 0.035714 | 1.75 | 1935-05-01 | 0.14286 | 1935-04-30 03:26 | 1933-12-28 08:00
Merseburg | Schkopau | 78.5 | 3.75 | 1 | 3.75 | 78.5 | 27 | 132.9643 | 135.8214 | 0.14286 | 0.75 | 1934-02-01 | 1.3333 | 1934-02-01 08:00 | 83.25 | 40 | 226.8214 | 230.5357 | 4.0357 | 1.75 | 1935-03-01 | 16.1429 | 1935-03-16 03:26 | 1934-02-01 08:00
Schkopau | Halle | 88.75 | 10.25 | 1 | 10.25 | 88.75 | 28 | 143.2143 | 143.5714 | 7.3929 | 1.75 | 1934-03-01 | 29.5714 | 1934-03-29 13:43 | 79.5 | 40 | 223.0714 | 230.5357 | 0.28571 | 1.75 | 1935-03-01 | 1.1429 | 1935-03-01 03:26 | 1934-03-29 13:43
Halle | Feutschenthal | 90.5 | 1.75 | 1 | 1.75 | 90.5 | 29 | 144.9643 | 151.0714 | 1.3929 | 1.75 | 1934-04-01 | 5.5714 | 1934-04-05 13:43 | 69.25 | 38 | 212.8214 | 216.7857 | 2.6786 | 1.5 | 1935-01-01 | 12.5 | 1935-01-12 12:00 | 1934-04-05 13:43
Feutschenthal | Eisleben | 108 | 17.5 | 1 | 17.5 | 108 | 31 | 162.4643 | 166.3214 | 3.6429 | 1.75 | 1934-06-01 | 14.5714 | 1934-06-14 13:43 | 67.5 | 38 | 211.0714 | 216.7857 | 0.92857 | 1.5 | 1935-01-01 | 4.3333 | 1935-01-04 08:00 | 1934-06-14 13:43
Eisleben | Helbra | 112 | 4 | 1 | 4 | 112 | 32 | 166.4643 | 174.0714 | 0.14286 | 1.75 | 1934-07-01 | 0.57143 | 1934-06-30 13:43 | 50 | 35 | 193.5714 | 197.0714 | 4.25 | 1.75 | 1934-10-01 | 17 | 1934-10-17 | 1934-06-30 13:43
Helbra | Kloster Mansfeld | 114 | 2 | 1 | 2 | 114 | 32 | 168.4643 | 174.0714 | 2.1429 | 1.75 | 1934-07-01 | 8.5714 | 1934-07-08 13:43 | 46 | 35 | 189.5714 | 197.0714 | 0.25 | 1.75 | 1934-10-01 | 1 | 1934-10-01 | 1934-07-08 13:43
Kloster Mansfeld | Hettstadt | 119 | 5 | 1 | 5 | 119 | 32 | 173.4643 | 174.0714 | 7.1429 | 1.75 | 1934-07-01 | 28.5714 | 1934-07-28 13:43 | 44 | 34 | 187.5714 | 189.3214 | 5.75 | 1.75 | 1934-09-01 | 23 | 1934-09-23 | 1934-07-28 13:43
Hettstadt | Stassfurt | 134 | 15 | 1 | 15 | 134 | 34 | 188.4643 | 189.3214 | 6.6429 | 1.75 | 1934-09-01 | 26.5714 | 1934-09-26 13:43 | 39 | 34 | 182.5714 | 189.3214 | 0.75 | 1.75 | 1934-09-01 | 3 | 1934-09-03 | 1934-07-05
Stassfurt | Salbke | 151 | 17 | 1 | 17 | 151 | 37 | 205.4643 | 210.1429 | 1.9643 | 1.5 | 1934-12-01 | 9.1667 | 1934-12-09 04:00 | 24 | 32 | 167.5714 | 174.0714 | 1.25 | 1.75 | 1934-07-01 | 5 | 1934-07-05 | 1934-04-28
Salbke | Buckau | 153 | 2 | 1 | 2 | 153 | 37 | 207.4643 | 210.1429 | 3.9643 | 1.5 | 1934-12-01 | 18.5 | 1934-12-18 12:00 | 7 | 29 | 150.5714 | 151.0714 | 7 | 1.75 | 1934-04-01 | 28 | 1934-04-28 | 1934-04-20
Buckau | Magdeburg Central | 155 | 2 | 1 | 2 | 155 | 37 | 209.4643 | 210.1429 | 5.9643 | 1.5 | 1934-12-01 | 27.8333 | 1934-12-27 20:00 | 5 | 29 | 148.5714 | 151.0714 | 5 | 1.75 | 1934-04-01 | 20 | 1934-04-20 | 1934-04-12
Magdeburg Central | Rothensee | 158 | 3 | 1 | 3 | 158 | 38 | 212.4643 | 216.7857 | 2.3214 | 1.5 | 1935-01-01 | 10.8333 | 1935-01-10 20:00 | 3 | 29 | 146.5714 | 151.0714 | 3 | 1.75 | 1934-04-01 | 12 | 1934-04-12 | 1934-04-01
Start Date, Working Up Line |  |  |  |  | 0 | 0 | [8 empty] | 0 | 28 |  | -143.5714 |  |  | 1934-04-01 |  | 1934-04-01
[14 empty] | 1 |  |  |  | 0 |  |  |  |  | 0
Two-End Completion Date
Section Difficulty: 1 is average difficulty so normal tracklaying rate; higher #s more difficult so rate slower
Enter tracklaying rates for each month on MonthRates page
Enter start date in form MM/DD/19YY
spreadsheet created by Iver Cooper.
Formulas:
First Date Completion Month = DATE(YEAR([Working Down Completion Date]),MONTH([Working Down Completion Date]),1)
First Date Completion Month = OFFSET(MonthRates!$A6,[Match Row Dn]-2,0,1,1)
Working Down Completion Date = [First Date Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
First Date in Completion Month = OFFSET(MonthRates!$A6,[Match Row Up]-2,0,1,1)
First Date in Completion Month = DATE(YEAR([Working Up Completion Date]),MONTH([Working Up Completion Date]),1)
Working Up Completion Date = [First Date in Completion Month]-1+([Miles Needed in Completion Month]*7/[Rate in Completion Month])
Two end date at B column station = IF([Working Down Completion Date]<[Working Up Completion Date, row below],[Working Down Completion Date],[Working Up Completion Date, row below])
Note on H2: Iver Cooper: row of prior month, no +1 because this has to be exact match
Note on Q22: Iver Cooper: no +1 because this has to be exact match
Note on Q4: Iver Cooper: +1 is wrong if lookup value = match value
Note on K1: Iver Cooper: Can be neg if start and complete in same mo and start after 1st.
Note on J2: Iver Cooper: lost miles = end of month prior to start month
Note on J3: Iver Cooper: lost miles from day 1 of start month to day before start
Note on M2: Iver Cooper: first day of start month
Note on O3: Iver Cooper: lost days in start month

## MonthRates
Track Laying Rates | [6 empty] | Test purposes
[7 empty] | 1st Day | 1933-07-01 | 1933-07-01 | 19
Month | Track Laying Rate (mi/wk) | Days in Month | Possible Effective Miles in Month | Cumulative Possible Effective Miles in Month | Cumulative Possible Track Days by End Month |  | Day # in Month |  | Cum Eff Miles, from Constr Date | Cum Eff Miles Nominal
|  |  | 0 | 0 | 0
Dummy Row |  |  | 0 | 0 | 0 | 1
1932-01-01 | 1.25 | 31 | 5.5357 | 5.5357 | 31 | 2 | 1 | 1 | 110.9286 | 110.9286
1932-02-01 | 1.25 | 29 | 5.1786 | 10.7143 | 60 | 3 | 2 | 2 | 111.1786 | 111.1786
1932-03-01 | 1.25 | 31 | 5.5357 | 16.25 | 91 | 4 | 3 | 3 | 111.4286 | 111.4286
1932-04-01 | 1.25 | 30 | 5.3571 | 21.6071 | 121 | 5 | 4 | 4 | 111.6786 | 111.6786
1932-05-01 | 1.25 | 31 | 5.5357 | 27.1429 | 152 | 6 | 5 | 5 | 111.9286 | 111.9286
1932-06-01 | 1.25 | 30 | 5.3571 | 32.5 | 182 | 7 | 6 | 6 | 112.1786 | 112.1786
1932-07-01 | 1.25 | 31 | 5.5357 | 38.0357 | 213 | 8 | 7 | 7 | 112.4286 | 112.4286
1932-08-01 | 1.25 | 31 | 5.5357 | 43.5714 | 244 | 9 | 8 | 8 | 112.6786 | 112.6786
1932-09-01 | 1.25 | 30 | 5.3571 | 48.9286 | 274 | 10 | 9 | 9 | 112.9286 | 112.9286
1932-10-01 | 1.25 | 31 | 5.5357 | 54.4643 | 305 | 11 | 10 | 10 | 113.1786 | 113.1786
1932-11-01 | 1.5 | 30 | 6.4286 | 60.8929 | 335 | 12 | 11 | 11 | 113.4286 | 113.4286
1932-12-01 | 1.5 | 31 | 6.6429 | 67.5357 | 366 | 13 | 12 | 12 | 113.6786 | 113.6786
1933-01-01 | 1.5 | 31 | 6.6429 | 74.1786 | 397 | 14 | 13 | 13 | 113.9286 | 113.9286
1933-02-01 | 1.5 | 28 | 6 | 80.1786 | 425 | 15 | 14 | 14 | 114.1786 | 114.1786
1933-03-01 | 1.75 | 31 | 7.75 | 87.9286 | 456 | 16 | 15 | 15 | 114.4286 | 114.4286
1933-04-01 | 1.75 | 30 | 7.5 | 95.4286 | 486 | 17 | 16 | 16 | 114.6786 | 114.6786
1933-05-01 | 1.75 | 31 | 7.75 | 103.1786 | 517 | 18 | 17 | 17 | 114.9286 | 114.9286
1933-06-01 | 1.75 | 30 | 7.5 | 110.6786 | 547 | 19 | 18 | 18 | 115.1786 | 115.1786
1933-07-01 | 1.75 | 31 | 7.75 | 118.4286 | 578 | 20 | 19 | 19 | 115.4286 | 115.4286
1933-08-01 | 1.75 | 31 | 7.75 | 126.1786 | 609 | 21 | 20 | 20 | 115.6786 | 115.6786
1933-09-01 | 0 | 30 | 0 | 126.1786 | 639 | 22 | 21 | 21 | 115.9286 | 115.9286
1933-10-01 | 0 | 31 | 0 | 126.1786 | 670 | 23 | 22 | 22 | 116.1786 | 116.1786
1933-11-01 | 0 | 30 | 0 | 126.1786 | 700 | 24 | 23 | 23 | 116.4286 | 116.4286
1933-12-01 | 0.75 | 31 | 3.3214 | 129.5 | 731 | 25 | 24 | 24 | 116.6786 | 116.6786
1934-01-01 | 0.75 | 31 | 3.3214 | 132.8214 | 762 | 26 | 25 | 25 | 116.9286 | 116.9286
1934-02-01 | 0.75 | 28 | 3 | 135.8214 | 790 | 27 | 26 | 26 | 117.1786 | 117.1786
1934-03-01 | 1.75 | 31 | 7.75 | 143.5714 | 821 | 28 | 27 | 27 | 117.4286 | 117.4286
1934-04-01 | 1.75 | 30 | 7.5 | 151.0714 | 851 | 29 | 28 | 28 | 117.6786 | 117.6786
1934-05-01 | 1.75 | 31 | 7.75 | 158.8214 | 882 | 30 | 29 | 29 | 117.9286 | 117.9286
1934-06-01 | 1.75 | 30 | 7.5 | 166.3214 | 912 | 31 | 30 | 30 | 118.1786 | 118.1786
1934-07-01 | 1.75 | 31 | 7.75 | 174.0714 | 943 | 32 | 31 | 31 | 118.4286 | 118.4286
1934-08-01 | 1.75 | 31 | 7.75 | 181.8214 | 974 | 33
1934-09-01 | 1.75 | 30 | 7.5 | 189.3214 | 1004 | 34
1934-10-01 | 1.75 | 31 | 7.75 | 197.0714 | 1035 | 35
1934-11-01 | 1.5 | 30 | 6.4286 | 203.5 | 1065 | 36
1934-12-01 | 1.5 | 31 | 6.6429 | 210.1429 | 1096 | 37
1935-01-01 | 1.5 | 31 | 6.6429 | 216.7857 | 1127 | 38
1935-02-01 | 1.5 | 28 | 6 | 222.7857 | 1155 | 39
1935-03-01 | 1.75 | 31 | 7.75 | 230.5357 | 1186 | 40
1935-04-01 | 1.75 | 30 | 7.5 | 238.0357 | 1216 | 41
1935-05-01 | 1.75 | 31 | 7.75 | 245.7857 | 1247 | 42
1935-06-01 | 1.75 | 30 | 7.5 | 253.2857 | 1277 | 43
1935-07-01 | 1.75 | 31 | 7.75 | 261.0357 | 1308 | 44
1935-08-01 | 1.75 | 31 | 7.75 | 268.7857 | 1339 | 45
1935-09-01 | 1.75 | 30 | 7.5 | 276.2857 | 1369 | 46
1935-10-01 | 1.75 | 31 | 7.75 | 284.0357 | 1400 | 47
1935-11-01 | 1.5 | 30 | 6.4286 | 290.4643 | 1430 | 48
1935-12-01 | 1.5 | 31 | 6.6429 | 297.1071 | 1461 | 49
1936-01-01 | 1.5 | 31 | 6.6429 | 303.75 | 1492 | 50
1936-02-01 | 1.5 | 29 | 6.2143 | 309.9643 | 1521 | 51
1936-03-01 | 1.5 | 31 | 6.6429 | 316.6071 | 1552 | 52
1936-04-01 | 1.75 | 30 | 7.5 | 324.1071 | 1582 | 53
1936-05-01 | 1.75 | 31 | 7.75 | 331.8571 | 1613 | 54
1936-06-01 | 1.75 | 30 | 7.5 | 339.3571 | 1643 | 55
1936-07-01 | 1.75 | 31 | 7.75 | 347.1071 | 1674 | 56
1936-08-01 | 1.75 | 31 | 7.75 | 354.8571 | 1705 | 57
1936-09-01 | 1.75 | 30 | 7.5 | 362.3571 | 1735 | 58
1936-10-01 | 1.75 | 31 | 7.75 | 370.1071 | 1766 | 59
1936-11-01 | 1.75 | 30 | 7.5 | 377.6071 | 1796 | 60
1936-12-01 | 1.75 | 31 | 7.75 | 385.3571 | 1827 | 61
spreadsheet created by Iver Cooper
Formulas:
Days in Month = EOMONTH([Month],0)-[Month]+1